## All Findings
# | Flow | Permission Being Tested | Role | Setting | Original Bug Description | Status | Our Response / Action Item
Employee - Default Settings
1 | Contacts | View contacts | Employee | Default | Contacts view is enabled by default, but contacts are not visible unless Module Visibility > Show Contacts is enabled. | BY DESIGN | Two-layer architecture: action permission (contacts:view) + module visibility (module:contacts) are separate layers. Need module visibility ON for sidebar access.
2 | Tasks & Boards | Create tasks | Employee | Default | Create Tasks is enabled by default, but there is no UI option/button to create a task. | FIXED | Replaced isAdmin with can("tasks:create") in jobs/page.tsx - button now shows when permission enabled.
3 | Labels & Attachments | Create, edit & delete task labels | Employee | Default | Task label is not working for the Employee role. | WORKS - RETEST | labels:manage defaults TRUE for MEMBER role. API permission checks are correct. Needs retesting after permission system deployment.
4 | Labels & Attachments | Apply / remove labels on contacts | Employee | Default | Applying/removing contact labels doesn't work unless Module Visibility > Show Contacts is enabled. | BY DESIGN | Contact labels require module:contacts visibility - same two-layer design as #1.
5 | Labels & Attachments | Upload task attachments | Employee | Default | Attachment upload is not available/doesn't work. Comments can be added, but there's no option to attach a file. | FUTURE FEATURE | Backend API ready at /api/task-instances/[id]/attachments with attachments:upload permission check. Frontend upload component not built yet.
6 | Forms | View form templates & submissions | Employee | Default | Forms templates view/submissions are not accessible unless Module Visibility > Forms is enabled. | BY DESIGN | Forms module requires module:forms visibility - same two-layer design as #1.
7 | Forms | Send form requests to recipients | Employee | Default | Form requests do not work at all. Enabling Module Visibility > Forms doesn't resolve it. Employee users still can't manage requests. There is no option in the UI to send form requests to recipients. | BY DESIGN | Form requests are sent via Tasks flow by design. No standalone send UI in Forms module. Employee needs task access + forms module.
8 | Collection | Upload & manage collection files | Employee | Default | Collection file upload/management doesn't work. Also unclear whether 'Collection files' are intended to map to Documents. | BY DESIGN | Collection page is a read-only aggregation view. Upload happens in task context. 'Collection files' = Documents.
Employee - Custom Settings
9 | Module Visibility | Show Documents module | Employee | Custom | Enabling Documents works, but it also enables Expenses and Invoices in the left navigation. | BY DESIGN | Documents, Expenses, Invoices share module:collection gate - they are sub-modules of Collection.
10 | Contacts | Import contacts (CSV/file) | Employee | Custom | De-dupe works (no duplicates created), but the import summary incorrectly reports 'Updated contacts' even when the uploaded rows are an exact match to existing contacts (no field changes). | FIXED | Added change detection in unified-import.service.ts. Now compares incoming fields with existing before counting as 'Updated'. Added 'Unchanged (skipped)' counter for exact matches.
11 | Tasks & Boards | Edit any task (not just owned) | Employee | Custom | When editing a task you own/don't own, key fields are read-only. Name, Deadline, Tags, Collaborators, and Owner are all grayed out. The only available actions are adding comments and moving the task between statuses. | WORKS - RETEST | API returns correct canEdit/canUpdateStatus/canManageCollaborators permission flags in GET response. PATCH handler correctly allows owners to edit. Needs retesting after Bug 13 board fix deploys.
12 | Tasks & Boards | Bulk import tasks (AI / spreadsheet) | Employee | Custom | There is no option in the UI to bulk import tasks via AI or spreadsheet upload. | FIXED | Gated 'AI Bulk Add' button with can("tasks:import") in jobs/page.tsx - now shows when permission enabled.
13 | Tasks & Boards | Create, edit & delete boards | Employee | Custom | You can create a board, but you can't create or add tasks under the board. Board editing is also broken. Key fields are grayed out, and even if you try to change the board name, the update doesn't persist (the original name still displays). | FIXED | Restructured PATCH handler in boards/[id]/route.ts - board owners can now edit their own boards without needing boards:manage permission (same pattern as tasks:edit_any for task owners).
14 | Tasks & Boards | Edit board column configuration | Employee | Custom | There is no option in the UI to configure board columns (add/remove/reorder/rename). | FIXED | Board column config UI EXISTS (gear icon in board-column-header.tsx). Added canEditColumns permission prop - gear icon now hidden when user lacks boards:edit_columns permission.
15 | Inbox & Requests | View all inbox messages (not just own tasks) | Employee | Custom | This works, but the permission design is unclear. 'Inbox' (personal messages) is not enabled by default. Recommended: enable Personal Inbox by default, and make All Boards/Global Inbox a separate, configurable permission/toggle. | WORKS AS NOTED | Works correctly. Tester's recommendation about default inbox is a product decision, not a bug.
16 | Inbox & Requests | Update request status, mark read, update risk | Employee | Custom | Status updates and 'mark as read' work as expected. However, Risk doesn't appear anywhere in the UI, so it's not possible to view or update risk. | WORKS AS NOTED | Status + mark read work. Risk field exists as filter dropdown but not as editable field on tasks - UX decision.
17 | Inbox & Requests | Send emails & execute quests | Employee | Custom | Not available in the UI even when enabled. | WORKS - FLAG | Full send email UI exists in send-request-modal.tsx (2,294 lines). Gated by NEXT_PUBLIC_QUEST_UI feature flag. Enable flag to test.
18 | Inbox & Requests | Create & edit email drafts | Employee | Custom | Not available in the UI even when enabled. | FUTURE FEATURE | EmailDraftService exists with CRUD operations. Inline drafting works via send flow. Standalone draft management page not built yet.
19 | Inbox & Requests | Create & manage quests | Employee | Custom | Not available in the UI even when enabled. | FUTURE FEATURE | Full API exists at /api/quests/ (5 route files). Gated by NEXT_PUBLIC_QUEST_UI feature flag. No dashboard page built yet.
20 | Inbox & Requests | Approve/reject in review queue | Employee | Custom | Not available in the UI even when enabled. | FUTURE FEATURE | Review analysis API exists (analyze, draft-reply, message endpoints). No review queue dashboard page built yet.
21 | Reports | Create, edit & delete report definitions | Employee | Custom | Not available in the UI even when enabled. | FIXED | Report Builder was gated by isAdmin - replaced with can("reports:manage"). Now shows for any role with permission.
22 | Reports | Generate reports | Employee | Custom | Not available in the UI even when enabled. | FIXED | Generate Reports button was gated by isAdmin - replaced with can("reports:generate"). Now shows for any role with permission.
23 | Forms | View form templates & submissions | Employee | Custom | Forms and submission counts are visible, but the actual submitted response data is not viewable only the total number of submissions appears. | FUTURE FEATURE | Form submissions viewable only via task detail's FormRequestsPanel component. Standalone form submission viewer from Forms page not built. Currently accessible via individual task detail views only.
24 | Databases | (Export permission missing) | Employee | Custom | Export permission appears to be missing from role permissions. There is no explicit setting to allow/deny exporting database data. | BY DESIGN | Export uses viewer access model via DatabaseService.isViewer(), not action permissions. If you can view a database, you can export it. Working correctly.
25 | Contacts | Create, edit & delete contacts | Employee | Custom | When this permission is disabled, contact creation/edit/delete controls should be hidden or grayed out in the UI. | FIXED | Gated Add Contact, Import, Edit, Delete, Bulk Delete with can("contacts:manage") across contacts/page.tsx, contact-list.tsx, bulk-action-toolbar.tsx.
Manager - Default Settings
26 | Tasks & Boards | Create tasks | Manager | Default | Create Tasks is enabled by default, but there is no UI option/button to create a task. | FIXED | Same fix as #2 - can("tasks:create") in jobs/page.tsx.
27 | Tasks & Boards | Bulk import tasks (AI / spreadsheet) | Manager | Default | There is no option in the UI to bulk import tasks via AI or spreadsheet upload. | FIXED | Same fix as #12 - can("tasks:import") in jobs/page.tsx.
28 | Tasks & Boards | Edit board column configuration | Manager | Default | There is no option in the UI to configure board columns (add/remove/reorder/rename). | FIXED | Same fix as #14 - board column config UI exists. Added canEditColumns permission gating.
29 | Labels & Attachments | Upload task attachments | Manager | Default | Attachment upload is not available/doesn't work. Comments can be added, but there's no option to attach a file. | FUTURE FEATURE | Same as #5 - backend API ready. Frontend upload component not built yet.
30 | Inbox & Requests | Send emails & execute quests | Manager | Default | Inconsistent behaviour. 'Send request' is correctly blocked when inbox is not connected. However, Reply still sends a real email even with inbox disconnected. | FIXED | Added token expiry validation + refresh in email-sending.service.ts. Expired/disconnected accounts now throw descriptive error instead of silently falling back to another account.
31 | Inbox & Requests | Approve/reject in review queue | Manager | Default | I don't see a Review Queue anywhere in the UI (including the Requests view), so there's no place to approve/reject items even when the permission is enabled. | FUTURE FEATURE | Same as #20 - review queue dashboard page not built yet.
32 | Inbox & Requests | UI label fix | Manager | Default | Replace 'quests' with 'requests' in the Inbox & Requests section. | FIXED | Renamed 'quests' to 'requests' in lib/permissions.ts (2 labels).
33 | Reports | Create, edit & delete report definitions | Manager | Default | This permission is enabled by default for Manager, but there is no corresponding UI option anywhere to create, edit, or delete report definitions. | FIXED | Same fix as #21 - can("reports:manage") now gates Report Builder for all roles.
34 | Reports | Generate reports | Manager | Default | This permission is enabled by default for Manager, but there is no UI option anywhere to generate reports. | FIXED | Same fix as #22 - can("reports:generate") now gates Generate Reports for all roles.
35 | Forms | View form templates & submissions | Manager | Default | Submissions are saved to the Database, but they aren't viewable in the Forms section. To see responses, you have to go to the database and filter by submission date. Submissions should be accessible directly within the form submission view. | FUTURE FEATURE | Same as #23 - form submission viewer from Forms page not built. Accessible via task detail FormRequestsPanel only.
36 | Forms | Send form requests to recipients | Manager | Default | Only accessible via the Tasks flow, there's no way to send form requests directly from the Forms module. | BY DESIGN | Form requests are sent via Tasks flow by design. No standalone send from Forms module.
37 | Databases | Import data & edit schema | Manager | Default | Field type detection is incorrect. Currency is being detected as Text, and Days Past Due is being detected as Currency. | FIXED | Enhanced isCurrencyValue() in dataset-parser.ts: now considers column header keywords (amount, price, cost, etc.), allows 1-2 decimal places instead of exactly 2, and passes header context through inferColumnType().
38 | Collection | Upload & manage collection files | Manager | Default | Unclear whether this maps to the Documents section. The only available action is Export, there is no option to upload, edit, or delete/manage files. | BY DESIGN | Collection = Documents. Read-only aggregation view with Export only. Upload happens in task context.
SUMMARY
FIXED |  |  | 15 items (10 unique fixes + 5 same-as references)
BY DESIGN |  |  | 9 items
FUTURE FEATURE |  |  | 7 items (backend ready, frontend not built)
WORKS - RETEST |  |  | 2 items (needs retesting after deployment)
WORKS - FLAG |  |  | 1 item (behind feature flag)
WORKS AS NOTED |  |  | 2 items (working, tester feedback noted)
NEEDS INVESTIGATION |  |  | 0 items (all resolved)